## Sheet1
Recursos | Salario | Horas laborales | Horas reales | Precio por hora | Precio por día
Project manager | 25000 | 160 | 120 | 208.3333 | 1250
UI Designer básico | 15000 | 160 | 120 | 125 | 750
Front-end developer | 30000 | 160 | 120 | 250 | 1500
Back-end developer | 40000 | 160 | 120 | 333.3333 | 2000
Database administrator | 20000 | 160 | 120 | 166.6667 | 1000
Quality Assurance Tester | 20000 | 160 | 120 | 166.6667 | 1000
DevOps Engineer | 30000 | 160 | 120 | 250 | 1500
Payment integration specialist | 30000 | 160 | 120 | 250 | 1500
Security Specialist | 25000 | 160 | 120 | 208.3333 | 1250
Costo de equipo | 50000 | 160 | 120 | 416.6667 | 2500
Alcance | Días programados | Días reales | Recursos | Capacidad | Precio
Pantalla de login | 2 | 2.9 | UI Designer básico | 50% | 1087.5
|  |  | Front-end developer | 30% | 1305
|  |  | Back-end developer | 30% | 1740
|  |  | DevOps Engineer | 20% | 870
Menú (vista cliente y administrador) | 15 | 21.75 | UI Designer básico | 80% | 13050
|  |  | Project manager | 90% | 24468.75
|  |  | Front-end developer | 80% | 26100
|  |  | Back-end developer | 80% | 34800
|  |  | Database administrator | 80% | 17400
|  |  | Quality Assurance Tester | 70% | 15225
|  |  | DevOps Engineer | 80% | 26100
Pantalla personalizar bebida | 3 | 4.35 | UI Designer básico | 30% | 978.75
|  |  | Front-end developer | 20% | 1305
|  |  | Back-end developer | 20% | 1740
Pantalla de pago | 10 | 14.5 | Project manager | 90% | 16312.5
|  |  | UI Designer básico | 40% | 4350
|  |  | Front-end developer | 80% | 17400
|  |  | Back-end developer | 80% | 23200
|  |  | Database administrator | 80% | 11600
|  |  | Quality Assurance Tester | 70% | 10150
|  |  | DevOps Engineer | 80% | 17400
|  |  | Payment integration specialist | 90% | 19575
Programa de acumulación de puntos | 8 | 11.6 | Project manager | 60% | 8700
|  |  | UI Designer básico | 30% | 2610
|  |  | Front-end developer | 60% | 10440
|  |  | Back-end developer | 80% | 18560
|  |  | Database administrator | 80% | 9280
|  |  | DevOps Engineer | 60% | 10440
Pantalla votar platillo | 2 | 2.9 | UI Designer básico | 50% | 1087.5
|  |  | Front-end developer | 30% | 1305
|  |  | Back-end developer | 30% | 1740
Precio operativo | 40 | 58 |  | 50% | 72500
Precio total |  |  |  |  | 422820
IVA |  |  |  |  | 67651.2
Precio total real |  |  |  |  | 490471.2